## Dashboard
CommerceOps — Master Progress Dashboard
Baseline | Master v1.0 + Inventory Slice v1.0 — 17 Aug 2026
Total tracked items | Total tracked items | Foundation specs approved | Foundation specs approved | Epics | Epics
92 |  | 24 |  | 8
Features | Features | User Stories | User Stories | Implementation done | Implementation done
43 |  | 9 |  | 0
Type | Total | Approved Specs | Implementation Done
Foundation | 24 | 24 | 0
Epic | 8 | 1 | 0
Feature | 43 | 1 | 0
Story | 9 | 9 | 0
Task | 8 | 8 | 0
Current Next Step | ID | Spec Weight | Reason
Execute engineering bootstrap | BOOT-001..008 | Lean | Establish the minimal runnable platform and CI baseline
Start first business story | INV-US001 | Story-only | Create query-driven protected inventory context
Implement controlled adjustment | INV-US002..009 | Story-only | Complete INV-F03 through small reviewable batches

## Master Tracker
ID | Type | Parent ID | Name | Priority | Spec Required | Spec Status | Spec Version | Implementation Status | Agent Plan Status | Test Status | Review Status | DoD Status | Dependencies | ADR | Owner | GitHub Issue | PR | Notes / Blockers
FND-001 | Foundation |  | Product Vision & Objectives | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-002 | Foundation |  | Scope & Product Boundaries | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-003 | Foundation |  | Technology Stack | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-004 | Foundation |  | System Architecture | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-005 | Foundation |  | Frontend Architecture | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-006 | Foundation |  | Backend Architecture | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-007 | Foundation |  | Data Architecture | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-008 | Foundation |  | API Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-009 | Foundation |  | State Management Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-010 | Foundation |  | UI & Design-System Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-011 | Foundation |  | Accessibility Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-012 | Foundation |  | Security & RBAC Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-013 | Foundation |  | Error Handling & Resilience | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-014 | Foundation |  | Performance Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-015 | Foundation |  | Observability Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-016 | Foundation |  | Testing Strategy | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-017 | Foundation |  | Coding Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-018 | Foundation |  | Documentation Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-019 | Foundation |  | Repository & Monorepo Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-020 | Foundation |  | CI/CD & Quality Gates | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-021 | Foundation |  | AI Coding-Agent Standards | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-022 | Foundation |  | Lean Spec-Driven Development Process | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-023 | Foundation |  | Definition of Done | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
FND-024 | Foundation |  | Non-Functional Requirements | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Foundation baseline approved in Master Spec v1.0
EPIC-01 | Epic |  | Authentication & User Access | Must | Full | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met | Foundation baseline |  | Engineer
AUTH-F01 | Feature | EPIC-01 | Sign-in and session establishment | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
AUTH-F02 | Feature | EPIC-01 | Session refresh, expiry and logout | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
AUTH-F03 | Feature | EPIC-01 | Authenticated user context and profile | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
AUTH-F04 | Feature | EPIC-01 | Protected routes and unauthorized states | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
AUTH-F05 | Feature | EPIC-01 | Authentication failure and recovery UX | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
EPIC-02 | Epic |  | Product Catalog Management | Must | Full | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met | Foundation baseline |  | Engineer
PROD-F01 | Feature | EPIC-02 | Product list, search, filter, sort and pagination | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
PROD-F02 | Feature | EPIC-02 | Product detail view | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
PROD-F03 | Feature | EPIC-02 | Create and edit product | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
PROD-F04 | Feature | EPIC-02 | Variant, SKU and pricing management | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
PROD-F05 | Feature | EPIC-02 | Product status / publish controls | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
PROD-F06 | Feature | EPIC-02 | Bulk product operations | Should | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
EPIC-03 | Epic |  | Inventory Management | Must | Full | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | Foundation baseline |  | Engineer
INV-F01 | Feature | EPIC-03 | Inventory list and operational filtering | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
INV-F02 | Feature | EPIC-03 | Inventory detail by SKU and location | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
INV-F03 | Feature | EPIC-03 | Controlled stock adjustment | Must | Full | Approved | v1.0 | Not Started | Not Started | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Full Feature Spec approved in CommerceOps EPIC-03 Inventory Development Specification v1.0
INV-F04 | Feature | EPIC-03 | Optimistic update and concurrency conflict handling | Must | Full | Backlog |  | Not Started | Not Started | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted |  |  | Recommended immediately after INV-F03 to exercise concurrency handling
INV-F05 | Feature | EPIC-03 | Low-stock indicators and operational alerts | Should | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
INV-F06 | Feature | EPIC-03 | Inventory change history | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
EPIC-04 | Epic |  | Order Operations | Must | Full | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met | Foundation baseline |  | Engineer
ORD-F01 | Feature | EPIC-04 | Order list, search, filters and pagination | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
ORD-F02 | Feature | EPIC-04 | Order detail and timeline | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
ORD-F03 | Feature | EPIC-04 | Fulfilment workflow | Must | Full | Backlog |  | Not Started | Not Started | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
ORD-F04 | Feature | EPIC-04 | Order cancellation workflow | Must | Full | Backlog |  | Not Started | Not Started | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
ORD-F05 | Feature | EPIC-04 | Partial refund simulation | Must | Full | Backlog |  | Not Started | Not Started | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
ORD-F06 | Feature | EPIC-04 | Order operational history and audit trail | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
EPIC-05 | Epic |  | Customer Management | Must | Full | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met | Foundation baseline |  | Engineer
CUS-F01 | Feature | EPIC-05 | Customer list and search | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
CUS-F02 | Feature | EPIC-05 | Customer profile and account status | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
CUS-F03 | Feature | EPIC-05 | Address and contact information | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
CUS-F04 | Feature | EPIC-05 | Customer order history | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
CUS-F05 | Feature | EPIC-05 | Operational notes and restricted PII display | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
EPIC-06 | Epic |  | RBAC & Administration | Must | Full | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met | Foundation baseline |  | Engineer
RBAC-F01 | Feature | EPIC-06 | Role and permission model | Must | Full | Backlog |  | Not Started | Not Started | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
RBAC-F02 | Feature | EPIC-06 | User-to-role assignment | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
RBAC-F03 | Feature | EPIC-06 | Permission-aware navigation and controls | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
RBAC-F04 | Feature | EPIC-06 | Server-side authorization enforcement | Must | Full | Backlog |  | Not Started | Not Started | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
RBAC-F05 | Feature | EPIC-06 | Authorization test matrix and admin audit | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
EPIC-07 | Epic |  | Audit & Activity History | Must | Full | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met | Foundation baseline |  | Engineer
AUD-F01 | Feature | EPIC-07 | Global audit-event list | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
AUD-F02 | Feature | EPIC-07 | Filter and search audit records | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
AUD-F03 | Feature | EPIC-07 | Entity activity timelines | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
AUD-F04 | Feature | EPIC-07 | Before/after change metadata | Should | Full | Backlog |  | Not Started | Not Started | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
AUD-F05 | Feature | EPIC-07 | Request/correlation traceability | Must | Full | Backlog |  | Not Started | Not Started | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
EPIC-08 | Epic |  | Operations Dashboard | Must | Full | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met | Foundation baseline |  | Engineer
DASH-F01 | Feature | EPIC-08 | Operational KPI cards | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
DASH-F02 | Feature | EPIC-08 | Low-stock work queue | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
DASH-F03 | Feature | EPIC-08 | Pending order/fulfilment work queue | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
DASH-F04 | Feature | EPIC-08 | Recent operational activity | Should | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
DASH-F05 | Feature | EPIC-08 | Role-aware dashboard composition | Must | Lean | Backlog |  | Not Started | N/A | Not Started | Pending | Not Met |  |  | Engineer + Agent-assisted
BOOT-001 | Task | FOUNDATION | Repository scaffold | Must | Lean | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met |  |  | Engineer + Agent-assisted |  |  | Phase 0 bootstrap
BOOT-002 | Task | FOUNDATION | Web application baseline | Must | Lean | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | BOOT-001 |  | Engineer + Agent-assisted |  |  | Phase 0 bootstrap
BOOT-003 | Task | FOUNDATION | API baseline | Must | Lean | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | BOOT-001 |  | Engineer + Agent-assisted |  |  | Phase 0 bootstrap
BOOT-004 | Task | FOUNDATION | Database baseline | Must | Lean | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | BOOT-001; BOOT-003 |  | Engineer + Agent-assisted |  |  | Phase 0 bootstrap
BOOT-005 | Task | FOUNDATION | Authentication development baseline | Must | Lean | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | BOOT-002; BOOT-003; BOOT-004 |  | Engineer + Agent-assisted |  |  | Seed/dev auth sufficient for RBAC first slice
BOOT-006 | Task | FOUNDATION | Quality baseline | Must | Lean | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | BOOT-001; BOOT-002; BOOT-003 |  | Engineer + Agent-assisted |  |  | Vitest/RTL/API tests/Playwright
BOOT-007 | Task | FOUNDATION | CI baseline | Must | Lean | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | BOOT-006 |  | Engineer + Agent-assisted |  |  | GitHub Actions quality pipeline
BOOT-008 | Task | FOUNDATION | Documentation baseline | Must | Lean | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | BOOT-001..007 |  | Engineer + Agent-assisted |  |  | README, env example, run instructions
INV-US001 | Story | INV-F03 | View adjustment context | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | BOOT-001..008; INV-F02 context |  | Engineer + Agent-assisted |  |  | First business story
INV-US002 | Story | INV-F03 | Open controlled adjustment workflow | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | INV-US001 |  | Engineer + Agent-assisted |  |  | Accessible dialog/drawer
INV-US003 | Story | INV-F03 | Enter and validate an adjustment | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | INV-US002 |  | Engineer + Agent-assisted |  |  | Client validation + preview
INV-US004 | Story | INV-F03 | Submit a valid stock adjustment | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | INV-US003 |  | Engineer + Agent-assisted |  |  | Transactional API mutation + audit
INV-US005 | Story | INV-F03 | Refresh server state after success | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | INV-US004 |  | Engineer + Agent-assisted |  |  | TanStack Query ownership
INV-US006 | Story | INV-F03 | Handle validation, authorization and server failures | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | INV-US003; INV-US004 |  | Engineer + Agent-assisted |  |  | 400/403/404/409/422/5xx UX
INV-US007 | Story | INV-F03 | Prevent duplicate adjustment submission | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | INV-US004 |  | Engineer + Agent-assisted |  |  | Idempotency semantics
INV-US008 | Story | INV-F03 | Reject stale inventory version safely | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | INV-US004 | ADR-009 | Engineer + Agent-assisted |  |  | 409 baseline; enhanced UX in INV-F04
INV-US009 | Story | INV-F03 | View created adjustment in history | Must | Story-only | Approved | v1.0 | Not Started | N/A | Not Started | Approved | Not Met | INV-US004; INV-US005 |  | Engineer + Agent-assisted |  |  | Minimal history; matures in INV-F06

## Decision Register
ADR | Decision | Status | Area | Owner | Affected Items | Notes
ADR-001 | Separate NestJS domain API from Next.js web application | Accepted | System Architecture | Engineer | FND-004; all Epics
ADR-002 | TanStack Query owns remote/server state | Accepted | Frontend / State | Engineer | FND-005; FND-009
ADR-003 | Redux Toolkit restricted to explicit client-only cross-feature state; no RTK Query | Accepted | Frontend / State | Engineer | FND-009
ADR-004 | TypeScript 7 primary compiler; TS6 compatibility only for tooling that requires legacy compiler API | Accepted | Tooling | Engineer | FND-003; FND-017 | Review when TS 7.1/tooling ecosystem removes compatibility need
ADR-005 | Storybook scoped to packages/ui and reusable complex patterns | Accepted | UI Engineering | Engineer | FND-010
ADR-006 | Two-speed Full vs Lean Feature specification model | Accepted | Delivery Process | Engineer | FND-022; all Features
ADR-007 | Sentry + structured logs + Web Vitals as lean observability baseline | Accepted | Observability | Engineer | FND-014; FND-015
ADR-008 | PostgreSQL + Prisma relational persistence; no microservices/event platform in v1 | Accepted | Backend / Data | Engineer | FND-006; FND-007
ADR-009 | Inventory mutations use integer expectedVersion optimistic concurrency; stale versions return 409 and do not mutate | Accepted | Inventory | Engineer | INV-F03; INV-F04; INV-US008 | Baseline integrity rule approved in Inventory Development Spec v1.0; INV-F04 refines conflict UX.

## Reference
Category | Value | Definition
Lifecycle | Backlog | Item identified; detailed spec not started
Lifecycle | Drafting | Specification being authored
Lifecycle | Review | Specification ready for engineering review
Lifecycle | Approved | Specification is authoritative for implementation
Implementation | Not Started | No implementation work started
Implementation | Planned | Implementation plan / prerequisites prepared
Implementation | In Progress | Implementation actively underway
Implementation | Done | Implementation complete; DoD may still be checked separately
Implementation | Blocked | Cannot progress due to a documented blocker
Implementation | Deferred | Intentionally moved out of current delivery window
Priority | Must | Required for v1 or the learning baseline
Priority | Should | High value but can follow core v1 capability
Priority | Could | Optional/stretch capability
Spec Weight | Full | Complex/high-risk feature; use full Feature Spec and Agent Plan where useful
Spec Weight | Lean | Straightforward/low-risk feature; one-page Feature Spec
Spec Weight | Story-only | User Story sufficient under an already explicit Feature contract